## Sheet1
[5 empty] | Alex |  | Oscar |  | Christian |  | Niko |  | Sam |  | Long
Week | Task | Summary | Time start | Deadline | Todo | Done? | Todo | Done? | Todo | Done? | Todo | Done? | Todo | Done? | Todo | Done?
1 | Req Elicitation | Outline a list of requirements | 6.4.2021 | 8.4.2021 | x | x | x | x | x | x | x | x | x | x | x | x
| Req Diagram | Do Req Diagram | 8.4.2021 | 11.4.2021 | x | x | x | x
| Use case diagram | Do use case diagram | 8.4.2021 | 11.4.2021 |  |  |  |  | x | x | x | x
| Sequence diagrams | Do sequence diagram | 8.4.2021 | 11.4.2021 | [8 empty] | x | x | x | x
2 | Narrow and redo requirements |  | 18.4.2021 | 18.4.2021 | x | x | x | x | x | x | x | x | x | x | x | x
| Req Diagram |  | 18.4.2021 | 21.4.2021 | [8 empty] | x | x
| Block Diagram |  | 18.4.2021 | 21.4.2021 |  |  | x | x
| Internal block |  | 18.4.2021 | 21.4.2021 | [6 empty] | x
| Constraints |  | 18.4.2021 | 21.4.2021 | x | x
| Use case diagram |  | 18.4.2021 | 21.4.2021 | x | x
| Activity |  | 18.4.2021 | 21.4.2021 | [5 empty] | x |  |  |  |  | x
| Sequence diagrams |  | 18.4.2021 | 21.4.2021 |  |  |  |  | x | x